## Sheet1
Task | Module | Time Estimate | Actual Time | Status
Implement human print of game | Result | 1 | 1.2 | Done
Find a way to assign a game id | DataBridgeCSV | 2
Research email smtp options | EmailOutbox | 0.5 | 0.5 | Done
Add the residual value as member of Result | Result | 0.5 | 0.5 | Done
Data bridge to save more results from one call | DataBridgeCSV | 0.5 | 0.1 | Done
Result to save up to milisecond timestamp | Result | 0.3 | 0.2 | Done
Research python website scraper | LotoResultsScraper | 3
Foundation of a configs object | Configurator | 0.5 | 0.5 | Done
Implement configs object | Configurator | 0.5 | 0.2 | Done
Implement Email Sender | EmailOutbox | 1.5 |  | Done
Table and API for sent Emails | DataBridgeCSV | 1
Email outgoing ID | DataBridgeCSV | 0.3
Print games nicely in table format | Game | 1 |  | POSTPONED
Research OAUTH2 gmail API - check if feasable | EmailOutbox | 1 |  | POSTPONED
Email to multiple recipients | EmailOutbox | 0.5 | 0.5 | Done
Include Email Id in email subject | EmailOutbox | 0.5 | 0.5 | Done
Setup Testing Environment | Testing | 0.5
Set new result framework | Result | 2 | 2 | Done
Implement ResultSet object | Result | 2 | 1 | Done
Implement HTML print for Results/sets | Result | 1 | 1 | Done
Change Email to send html formats | EmailOutbox | 1 | 1 | Done
Setup new DataBridgeCSV | DataBridgeCSV | 3 | 3 | Done
Implement connectors object | DataBridgeCSV | 1 | 1 | Done
New objects to define wining combinations | ResultComparer | 1
New object to compare 2 results and determine wining combination | ResultComparer | 1